## tasks
task_id | task_title | sprint | story_points | complexity_class | planned_hours | actual_hours | participant_name | qualification | participant_hours | status | area | external_dependency | sprint_start | sprint_end
TASK-601 | Smart backlog planner | Спринт 6 | 13 | XL | 54 | 49 | Анна Смирнова | senior | 12 | completed | Analytics | FALSE | 2026-04-20 | 2026-05-03
TASK-601 | Smart backlog planner | Спринт 6 | 13 | XL | 54 | 49 | Иван Иванов | senior | 14 | completed | Analytics | FALSE | 2026-04-20 | 2026-05-03
TASK-601 | Smart backlog planner | Спринт 6 | 13 | XL | 54 | 49 | Елена Сидорова | analyst | 10 | completed | Analytics | FALSE | 2026-04-20 | 2026-05-03
TASK-602 | Dashboard anomaly alerts | Спринт 6 | 8 | L | 30 | 27 | Алексей Коваленко | middle | 12 | completed | Analytics | FALSE | 2026-04-20 | 2026-05-03
TASK-602 | Dashboard anomaly alerts | Спринт 6 | 8 | L | 30 | 27 | Иван Иванов | senior | 8 | completed | Analytics | FALSE | 2026-04-20 | 2026-05-03